## Start here
LisheBora pilot test – Makueni County, Kalulini school (demo data)
Purpose: AATF staff test every process end to end with demo accounts before real users are invited. All figures are illustrative.
Before you start
1. On the LisheBora computer run scripts\use-demo.bat (demo database), then scripts\start-test-server.bat. Three windows open (API, worker, website); keep them open and the computer awake.
2. The start window shows the address to share, e.g. http://192.168.x.x:3000. Testers on the same office network open it in their browser. Staff sign in at /sign-in; administrators at /admin/sign-in.
3. Every demo account uses the password: Demo!2026pass
4. Some roles ask for a 6-digit code. In demo mode the code is shown on the screen (no SMS is sent).
5. Use a separate browser (or a private window) per person so sessions do not mix; or sign out between roles.
6. The sourcing event must close more than 1 hour after it is submitted. Do stages 13 and 15 while you wait.
7. Fill the Result column (Pass / Fail / Blocked) and write what you saw in Comments. Log problems on the Issues sheet with a screenshot.
What is in the demo data
Real Makueni, Embu and Isiolo schools; demo accounts for every role in Makueni; two prequalified demo suppliers (Umoja cooperative, Tumaini traders); an Umoja aggregation hub and a county food store; illustrative reference prices; one older demo order (PO-DEMO-0001) for Kalulini and Muatini.
Want to see a finished cycle first?
scripts\use-example.bat switches to an example database in which the whole cycle below has already been done automatically (82 checks, all passed – see LisheBora_Simulation_Report.xlsx). Switch back with scripts\use-demo.bat before hands-on testing.
Controls
Rows marked ‘Control’ check that the system REFUSES something (e.g. approving your own request). A control passes when the action is blocked.

## Accounts
Email (sign-in) | Role | Area | Sign-in page | Used for | Password
admin@lishebora.local | Super Administrator | National | /admin/sign-in | Features & menus, administrator accounts (password ChangeMe!2026) | ChangeMe!2026
administrator@demo.lishebora | Administrator | National | /admin/sign-in | Readiness checklist, users, master data, website publishing | Demo!2026pass
editor@demo.lishebora | Content Editor | National | /sign-in | Drafts website news and pages (cannot publish) | Demo!2026pass
nutrition@demo.lishebora | Nutrition Officer | Makueni County | /sign-in | Creates the term menu | Demo!2026pass
procurement@demo.lishebora | County Procurement Officer | Makueni County | /sign-in | Approves menus, builds the plan, vets suppliers, runs sourcing | Demo!2026pass
meals.officer@demo.lishebora | School Meals Officer | Kalulini school | /sign-in | School demand, daily food use | Demo!2026pass
school.admin@demo.lishebora | School Administrator | Kalulini school | /sign-in | Approves demand, school GPS, confirms deliveries, complaints | Demo!2026pass
finance@demo.lishebora | County Finance Officer | Makueni County | /sign-in | Budget lines, budget confirmation, invoice approval | Demo!2026pass
county.admin@demo.lishebora | County Administrator | Makueni County | /sign-in | Approves plans, prequalifies suppliers, resolves cases | Demo!2026pass
approver@demo.lishebora | Approving Officer | Makueni County | /sign-in | Approves sourcing events and awards | Demo!2026pass
evaluator1@demo.lishebora | Evaluation Committee Member 1 | Makueni County | /sign-in | Declares conflict of interest, scores bids | Demo!2026pass
evaluator2@demo.lishebora | Evaluation Committee Member 2 | Makueni County | /sign-in | Scores bids | Demo!2026pass
evaluator3@demo.lishebora | Evaluation Committee Member 3 | Makueni County | /sign-in | Scores bids | Demo!2026pass
supplier1@demo.lishebora | Supplier – Umoja Farmers Cooperative (demo) | Own organisation | /sign-in | Bids, acknowledges orders, follows payment | Demo!2026pass
supplier2@demo.lishebora | Supplier – Tumaini Grain Traders (demo) | Own organisation | /sign-in | Competing bid, clarification question | Demo!2026pass
aggregator@demo.lishebora | Aggregator – Umoja hub | Umoja hub | /sign-in | Farmer intake, batches, transfers, invoices | Demo!2026pass
inspector@demo.lishebora | Quality Inspector | Makueni County | /sign-in | Inspects batches, recalls | Demo!2026pass
warehouse@demo.lishebora | Warehouse Officer | County food store | /sign-in | Stock counts at the county store | Demo!2026pass
warehouse.supervisor@demo.lishebora | Warehouse Supervisor | Makueni County | /sign-in | Verifies write-offs and counts | Demo!2026pass
logistics@demo.lishebora | Logistics Officer | Makueni County | /sign-in | Plans and dispatches delivery trips | Demo!2026pass
driver@demo.lishebora | Driver | Own trips | /sign-in | Updates trip progress | Demo!2026pass
accounts@demo.lishebora | Finance Officer – verifier | Makueni County | /sign-in | Verifies invoices, payment details | Demo!2026pass
payments@demo.lishebora | Finance Officer – payer | Makueni County | /sign-in | Records payments, IFMIS export | Demo!2026pass
meal@demo.lishebora | Programme MEAL Officer | Programme | /sign-in | MEAL dashboard, exports, map | Demo!2026pass
risk@demo.lishebora | Risk & Compliance Officer | Makueni County | /sign-in | Risk flags | Demo!2026pass
auditor@demo.lishebora | Auditor | National (read-only) | /sign-in | Audit trail | Demo!2026pass
school2.admin@demo.lishebora | School Administrator (Muatini) | Muatini school | /sign-in | Used only to check one school cannot act for another | Demo!2026pass
(registers on the website) | New supplier – your own test farmer group | Own organisation | /register | Self-registration, documents, bidding | choose your own

## Test script
# | Stage | Step | Type | Who | Account | Where in the system | What to do | Expected result | Result | Tester | Date | Comments
1 | 1 Set-up | Sign in as administrator | Process | Administrator | administrator@demo.lishebora | /admin/sign-in | Sign in with the password, then type the 6-digit code shown on the screen (demo mode). | The admin console opens.
2 | 1 Set-up | Administrator cannot use the staff sign-in | Control | Administrator | administrator@demo.lishebora | /sign-in | Try the administrator email on the normal sign-in page. | Refused with a message to use the administration sign-in.
3 | 1 Set-up | Check pilot readiness | Process | Administrator | administrator@demo.lishebora | Administration › Pilot readiness | Open the page and read the items. | The checklist loads with a percentage and Fix links (demo data is flagged – expected for this test).
4 | 1 Set-up | Record the school's location | Process | School Administrator | school.admin@demo.lishebora | Plan › School locations | Open Kalulini › Set location. On a phone at the school tap ‘Use my location’; otherwise click the school on the map or type the coordinates. Save. | Coordinates saved with ‘how captured’, your name and time.
5 | 1 Set-up | Wrong coordinates are refused | Control | School Administrator | school.admin@demo.lishebora | Plan › School locations | Type latitude 37.62 and longitude -1.80 (swapped) and save. | Refused: ‘outside Kenya … not swapped’.
6 | 2 Menu | Create the term menu | Process | Nutrition Officer | nutrition@demo.lishebora | Plan › Menus & terms | New menu: 5 days (Mon–Fri) with dishes and portions in grams (e.g. ugali, beans, sukuma wiki, oil, salt). | Menu saved as draft; the food-group summary shows whether it meets the diversity minimum.
7 | 2 Menu | Submit the menu | Process | Nutrition Officer | nutrition@demo.lishebora | Plan › Menus & terms | Submit the menu for validation. | Status ‘submitted’; appears in the procurement officer’s ‘My approvals’.
8 | 2 Menu | Cannot approve own menu | Control | Nutrition Officer | nutrition@demo.lishebora | Overview › My approvals | Look for an approve button on your own menu. | Not available / refused.
9 | 2 Menu | Return needs a reason | Control | County Procurement Officer | procurement@demo.lishebora | Overview › My approvals | Choose ‘Return’ without typing a reason. | Refused until a reason is given.
10 | 2 Menu | Approve the menu | Process | County Procurement Officer | procurement@demo.lishebora | Overview › My approvals | Approve the menu. | Menu status ‘approved’; it can now be chosen for school demand.
11 | 3 School demand | Record school demand | Process | School Meals Officer | meals.officer@demo.lishebora | Plan › School demand | New demand for Kalulini, Term 3 2026, the approved menu. Learners (pre-filled from enrolment, adjust if needed), attendance 95 %, 40 feeding days, wastage 3 %, food already in stock. | Quantities per food item are calculated; no red (blocking) flags.
12 | 3 School demand | Too many feeding days is blocked | Control | School Meals Officer | meals.officer@demo.lishebora | Plan › School demand | Change feeding days to 120 and try to submit. | Flag ‘feeding days’ and submission refused. Set it back to 40.
13 | 3 School demand | Submit the demand | Process | School Meals Officer | meals.officer@demo.lishebora | Plan › School demand | Submit. | Status ‘submitted’.
14 | 3 School demand | Cannot approve own demand | Control | School Meals Officer | meals.officer@demo.lishebora | Overview › My approvals | Check whether you can approve it. | Not possible.
15 | 3 School demand | Validate and approve the demand | Process | School Administrator | school.admin@demo.lishebora | Overview › My approvals | Validate, then approve (two steps). | Demand status ‘approved’.
16 | 3 School demand | Approved demand is locked | Control | School Meals Officer | meals.officer@demo.lishebora | Plan › School demand | Try to edit the approved demand. | Editing refused (locked).
17 | 4 Budget & plan | Create the budget line | Process | County Finance Officer | finance@demo.lishebora | Plan › Budgets | New budget line for Makueni, Term 3 dates, funding source, approved amount (test figure). | Budget line shows approved, committed and available amounts.
18 | 4 Budget & plan | Build the procurement plan | Process | County Procurement Officer | procurement@demo.lishebora | Plan › Procurement plans | Preview then create the plan for Makueni, Term 3 (grouped by county). Link the budget line. | Plan lists every food item with quantities, schools and estimated value; no unpriced lines.
19 | 4 Budget & plan | Submit the plan | Process | County Procurement Officer | procurement@demo.lishebora | Plan › Procurement plans | Submit. | Waits for the budget confirmation step.
20 | 4 Budget & plan | County admin cannot skip the finance step | Control | County Administrator | county.admin@demo.lishebora | Overview › My approvals | Try to approve before finance. | Refused / not shown yet.
21 | 4 Budget & plan | Confirm the budget | Process | County Finance Officer | finance@demo.lishebora | Overview › My approvals | Approve the budget step. | Moves to county approval.
22 | 4 Budget & plan | Approve the plan | Process | County Administrator | county.admin@demo.lishebora | Overview › My approvals | Approve. | Plan ‘approved’; budget line shows the amount earmarked.
23 | 5 Supplier onboarding | Register a new supplier | Process | New supplier | your new supplier account | Website › Register | Register a test farmer group with a mobile number you can use (or one made up for the test), Makueni County, the foods it supplies. Enter the SMS code shown on screen (demo mode). | Account created and signed in; profile status ‘submitted’.
24 | 5 Supplier onboarding | Upload documents | Process | New supplier | your new supplier account | Supplier › My supplier profile | Upload the registration certificate and bank letter (any PDF for the test). | Documents listed as ‘pending’.
25 | 5 Supplier onboarding | Review the supplier | Process | County Procurement Officer | procurement@demo.lishebora | Source › Supplier registry | Open the new supplier, mark ‘under review’, verify each document. | Documents ‘verified’.
26 | 5 Supplier onboarding | Procurement officer cannot approve suppliers | Control | County Procurement Officer | procurement@demo.lishebora | Source › Supplier registry | Try ‘approve’. | Refused – the county administrator approves.
27 | 5 Supplier onboarding | Approve and prequalify | Process | County Administrator | county.admin@demo.lishebora | Source › Supplier registry | Approve, then prequalify for its food categories (e.g. legumes, vegetables, fruits). | Status ‘prequalified’; the supplier can now bid.
28 | 6 Sourcing | Create the sourcing event | Process | County Procurement Officer | procurement@demo.lishebora | Plan › Procurement plans › (plan) or Source › Sourcing events | Create the event from the approved plan. Set the closing time at least 1 hour 15 minutes from now (the system requires more than 1 hour). | Draft event with one lot per food item.
29 | 6 Sourcing | Weights must add up to 100 | Control | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events | Set technical weight to 70 without changing price weight; save. | Refused.
30 | 6 Sourcing | Submit the event | Process | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events | Submit for approval. | Waits for the approving officer.
31 | 6 Sourcing | Cannot approve own event | Control | County Procurement Officer | procurement@demo.lishebora | Overview › My approvals | Check for approve. | Not possible.
32 | 6 Sourcing | Approve and publish | Process | Approving Officer | approver@demo.lishebora | Overview › My approvals | Approve. | Event ‘open’; visible on the public Opportunities page.
33 | 6 Sourcing | Suppliers are notified | Process | Supplier – Umoja Farmers Cooperative (demo) | supplier1@demo.lishebora | Account › Notifications | Check notifications. | ‘New opportunity’ notification.
34 | 6 Sourcing | Submit bids (3 suppliers) | Process | Supplier – Umoja Farmers Cooperative (demo) | supplier1@demo.lishebora | Supplier › Opportunities | Supplier 1, supplier 2 and your new supplier each open the event, enter prices for the lots they supply and submit. | Each gets a bid receipt number. The estimate is not shown to suppliers.
35 | 6 Sourcing | Bids stay sealed | Control | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events › (event) › Bids | Look at the bids before the closing time; try ‘Open bids’. | Only bidder names/receipts visible; opening refused before closing time.
36 | 6 Sourcing | Clarification question | Process | Supplier – Tumaini Grain Traders (demo) | supplier2@demo.lishebora | Supplier › Opportunities › (event) | Ask a question; then the procurement officer answers it. | All bidders see the answer.
37 | 6 Sourcing | Wait for the closing time | Process | — | — | — | Do other stages meanwhile (e.g. stage 13 complaints, website news). After the closing time passes: | Event shows ‘closed’.
38 | 6 Sourcing | Late bid refused; open bids | Process | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events › (event) | Try a late bid as supplier 1 (refused), then open the bids as procurement officer. | Bid register with prices.
39 | 6 Sourcing | Appoint 3 evaluators | Process | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events › (event) › Evaluation | Choose Evaluator One, Two and Three. Try adding yourself. | Panel saved; adding yourself refused (segregation of duties).
40 | 6 Sourcing | Declare conflict of interest and score | Process | Evaluation Committee Member 1 | evaluator1@demo.lishebora | Source › My evaluations | Each evaluator: declare no conflict, score every bid, submit. (Scoring before declaring is refused.) | Scores submitted by all three.
41 | 6 Sourcing | Consolidate | Process | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events › (event) | Consolidate the evaluation. | Ranking per lot with technical + price scores and a recommended total.
42 | 6 Sourcing | Recommend award | Process | County Procurement Officer | procurement@demo.lishebora | Source › Sourcing events › (event) | Recommend the award. | Goes to finance commitment check.
43 | 6 Sourcing | Finance commitment check, then award approval | Process | County Finance Officer | finance@demo.lishebora | Overview › My approvals | Finance approves; then the approving officer approves. (Approver cannot act before finance.) | Event ‘awarded’; award notice on the public Opportunities page.
44 | 7 Contract & order | Acknowledge the purchase order | Process | Supplier – Umoja Farmers Cooperative (demo) | supplier1@demo.lishebora | Supplier › My contracts & orders | Each winning supplier opens the contract and PO and acknowledges it. | PO status ‘acknowledged’.
45 | 7 Contract & order | Unsuccessful bidders informed | Process | Supplier – Tumaini Grain Traders (demo) | supplier2@demo.lishebora | Account › Notifications | Check notifications. | Outcome message received.
46 | 8 Aggregation & quality | Record farmer intake | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Fulfil › Aggregation & intake | Record produce received from 2 farmers (name, gender, youth, food, quantity) at the Umoja hub for the PO items. | A batch is created with the total quantity and producers.
47 | 8 Aggregation & quality | Request inspection | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Fulfil › Aggregation & intake | Request inspection for the batch. | Batch ‘awaiting inspection’.
48 | 8 Aggregation & quality | Inspect and clear | Process | Quality Inspector | inspector@demo.lishebora | Fulfil › Quality inspection | Enter moisture (e.g. 12.4 %), visual checks, grade, accepted quantity. | Batch ‘cleared’; supplier notified.
49 | 8 Aggregation & quality | Failed moisture cannot be accepted | Control | Quality Inspector | inspector@demo.lishebora | Fulfil › Quality inspection | For another batch of maize enter moisture 15.5 % and ‘accepted’. | Refused; record as rejected with a reason → exception case raised.
50 | 8 Aggregation & quality | Inspector cannot inspect own intake | Control | Quality Inspector | inspector@demo.lishebora | Fulfil › Aggregation & intake | Record an intake yourself and try to inspect it. | Refused (segregation of duties).
51 | 8 Aggregation & quality | Print the QR label | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Fulfil › Aggregation & intake › (batch) | Open the QR label. | QR label for the batch; scanning shows the public trace page.
52 | 9 Warehouse | Transfer stock to the county store | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Fulfil › Inventory | Transfer a small quantity from the hub to the county food store. | Stock appears at the county store.
53 | 9 Warehouse | Write-off needs verification | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Fulfil › Inventory | Record a 1 kg write-off (torn sack) and try to approve it yourself; then the warehouse supervisor approves. | Posted only after the supervisor verifies it.
54 | 9 Warehouse | Stock count | Process | Warehouse Officer | warehouse@demo.lishebora | Fulfil › Inventory | Count the county store; enter a quantity 1 kg lower than the system. | Variance shown; posted after the supervisor verifies.
55 | 10 Dispatch & delivery | Plan the delivery trip | Process | Logistics Officer | logistics@demo.lishebora | Fulfil › Dispatch | New trip from the hub to Kalulini with the cleared batches, vehicle, driver and date. Try sending more than ordered. | Over-sending refused; trip created.
56 | 10 Dispatch & delivery | Route suggestion | Process | Logistics Officer | logistics@demo.lishebora | Fulfil › Dispatch › (trip) | Open the suggested route. | Route with distance (uses the school GPS).
57 | 10 Dispatch & delivery | Dispatch the trip | Process | Logistics Officer | logistics@demo.lishebora | Fulfil › Dispatch | Dispatch. | Status ‘dispatched’; school and driver notified.
58 | 10 Dispatch & delivery | Driver updates progress | Process | Driver | driver@demo.lishebora | Fulfil › Deliveries | Mark ‘in transit’ (allow location on the phone). | Status ‘in transit’ with last position on the map.
59 | 10 Dispatch & delivery | Confirm delivery at school (e-POD) | Process | School Administrator | school.admin@demo.lishebora | Fulfil › Deliveries | Confirm what was received; reject 10 kg as damaged with a reason; sign on screen. | Delivery ‘partially accepted’; exception raised for the rejected goods.
60 | 10 Dispatch & delivery | Other school cannot confirm | Control | School Administrator (Muatini) | school2.admin@demo.lishebora | Fulfil › Deliveries | Muatini’s administrator looks for Kalulini’s delivery. | Not visible / refused.
61 | 10 Dispatch & delivery | Resolve the delivery exception | Process | County Administrator | county.admin@demo.lishebora | Oversight › Exceptions | Procurement adds a progress note; the county administrator resolves. | Case ‘resolved’.
62 | 11 School stock | Record daily food use | Process | School Meals Officer | meals.officer@demo.lishebora | Fulfil › Inventory | Record food used today and meals served. | School stock goes down.
63 | 11 School stock | Stock outlook | Process | School Meals Officer | meals.officer@demo.lishebora | Performance & finance › Forecasts & prices | Open the stock outlook. | Days of food left per item.
64 | 11 School stock | Trace a batch | Process | County Procurement Officer | procurement@demo.lishebora | Fulfil › Traceability | Search the batch code (or scan the QR). | Farmers → hub → inspection → school; the public page hides farmer names.
65 | 12 Invoice & payment | Submit the invoice | Process | Aggregator – Umoja hub | aggregator@demo.lishebora | Performance & finance › Invoices & payments | New invoice for the PO; try billing more than was accepted, then bill the accepted quantities. | Over-billing refused; invoice ‘matched’ (PO + delivery + invoice).
66 | 12 Invoice & payment | Duplicate invoice number refused | Control | Aggregator – Umoja hub | aggregator@demo.lishebora | Performance & finance › Invoices & payments | Submit another invoice with the same supplier invoice number. | Refused.
67 | 12 Invoice & payment | Verify the invoice | Process | Finance Officer – verifier | accounts@demo.lishebora | Overview › My approvals | Verify (three-way match). | Status ‘verified’; the same person cannot also approve.
68 | 12 Invoice & payment | Approve the invoice | Process | County Finance Officer | finance@demo.lishebora | Overview › My approvals | Approve for payment. | Status ‘approved’; supplier notified.
69 | 12 Invoice & payment | Verify payment details | Process | Finance Officer – verifier | accounts@demo.lishebora | Performance & finance › Payment integrations | The supplier updates its M-Pesa details; finance verifies them. | Details verified.
70 | 12 Invoice & payment | Record payment | Process | Finance Officer – payer | payments@demo.lishebora | Performance & finance › Invoices & payments | Record payment (e.g. two instalments with M-Pesa references). The verifier cannot pay. | Status ‘paid’; supplier notified; budget line shows paid.
71 | 12 Invoice & payment | IFMIS export | Process | Finance Officer – payer | payments@demo.lishebora | Performance & finance › Payment integrations | Download the IFMIS export. | CSV includes the invoice.
72 | 13 Complaints & recall | Raise and close a complaint | Process | School Administrator | school.admin@demo.lishebora | Performance & finance › Complaints | Raise a food-quality complaint about the supplier. Procurement investigates, supplier responds, county admin resolves, school confirms with a rating. | Complaint ‘closed’ with full history.
73 | 13 Complaints & recall | Public grievance | Process | Member of the public | no sign-in | Website › Contact | Send a grievance as a parent, choose Makueni. | Case number CMP-… given; appears in the county’s complaints.
74 | 13 Complaints & recall | Recall a batch | Process | Quality Inspector | inspector@demo.lishebora | Fulfil › Traceability › (batch) | Open the delivered batch and recall it with a reason. (A supplier cannot recall.) | Schools warned; QR page shows RECALLED; recorded use of that batch blocked.
75 | 14 Monitoring & audit | MEAL dashboard and exports | Process | Programme MEAL Officer | meal@demo.lishebora | Performance & finance › MEAL dashboard | Review reach, sourcing, finance; download Excel exports. | Figures reflect this test cycle.
76 | 14 Monitoring & audit | Supplier scorecards | Process | County Procurement Officer | procurement@demo.lishebora | Performance & finance › Supplier performance | Open the scorecards. | Umoja shows deliveries and a score.
77 | 14 Monitoring & audit | Price intelligence | Process | County Procurement Officer | procurement@demo.lishebora | Performance & finance › Forecasts & prices | Open prices (suppliers cannot see this page). | Median prices per food item.
78 | 14 Monitoring & audit | Risk flags | Process | Risk & Compliance Officer | risk@demo.lishebora | Oversight › Risk dashboard | Review flags and run a scan. | Flags listed (e.g. the recall).
79 | 14 Monitoring & audit | Programme map | Process | Programme MEAL Officer | meal@demo.lishebora | Performance & finance › Programme map | Open the map. | Kalulini, hub and store shown.
80 | 14 Monitoring & audit | Audit trail | Process | Auditor | auditor@demo.lishebora | Oversight › Audit trail | Search the actions done in this test. | Every action listed with who and when; nothing can be edited.
81 | 14 Monitoring & audit | Data scope | Control | School Administrator | school.admin@demo.lishebora | Any list page | Check lists show only Kalulini / Makueni. | No other school or county visible.
82 | 15 Website content | Draft and publish news | Process | Content Editor | editor@demo.lishebora | Administration › Website content | Write a news post and submit it (you cannot publish). | Waits for review.
83 | 15 Website content | Publish | Process | Administrator | administrator@demo.lishebora | Administration › Website content | Review and publish the post; edit and publish the homepage banner. | Live on the website.
84 | 16 Menus & access | Each role sees only its own pages | Process | Evaluation Committee Member 1 | evaluator1@demo.lishebora | Menu on the left | Sign in as several roles (e.g. evaluator, driver, school administrator) and look at the menu. | Only the pages listed on the Accounts sheet for that role (plus Dashboard, Notifications, My profile).
85 | 16 Menus & access | Hidden page cannot be opened by address | Control | Driver | driver@demo.lishebora | Browser address bar | As the driver, type …/app/invoices in the address bar. | Message ‘Not part of your account’.
86 | 16 Menus & access | Super Administrator adds a page for one person | Process | Super Administrator | admin@lishebora.local | Administration › Features & menus › By person | Choose Evaluator One, tick ‘Supplier registry’, save. Sign in as evaluator1. | Supplier registry now appears in Evaluator One’s menu.
87 | 16 Menus & access | A page the role does not allow cannot be added | Control | Super Administrator | admin@lishebora.local | Administration › Features & menus › By person | For Evaluator One try to tick ‘Invoices & payments’. | Cannot be ticked; shows which roles would allow it.
88 | 16 Menus & access | Change a role's standard menu | Process | Super Administrator | admin@lishebora.local | Administration › Features & menus › By role | Choose Driver, add ‘Complaints’, save; sign in as the driver; then ‘Reset to standard’. | Complaints appears for all drivers, and disappears after reset.
89 | 16 Menus & access | Administrator cannot change menus | Control | Administrator | administrator@demo.lishebora | Administration | As administrator@demo.lishebora look for Features & menus. | Not in the menu (Super Administrator only).

## Progress
Stage | Steps | Pass | Fail | Blocked | Not done
1 Set-up
2 Menu
3 School demand
4 Budget & plan
5 Supplier onboarding
6 Sourcing
7 Contract & order
8 Aggregation & quality
9 Warehouse
10 Dispatch & delivery
11 School stock
12 Invoice & payment
13 Complaints & recall
14 Monitoring & audit
15 Website content
16 Menus & access
Total

## Issues
# | Step # | Found by | Date | What happened | Expected | Severity | Screenshot / file | Status | Fixed in
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58